## Sheet1
Issue Type | Epic Name | Summary | Description | Epic Link | Parent | Labels | Acceptance Criteria
Epic | 0.1 Product Vision & Scope Finalization | 0.1 Product Vision & Scope Finalization | Define product boundaries, use cases, non-goals, success metrics, and release planning assumptions. |  |  | Epic scope approved
Story |  | Define MVP scope boundaries | Document what is included in MVP and what is explicitly excluded from the first product release. | 0.1 Product Vision & Scope Finalization |  | phase0,planning,scope | MVP inclusions and exclusions documented and approved
Sub-task |  | List MVP capabilities | Identify included flows: onboarding, enrichment, persona, scoring, output, and reporting. |  | Define MVP scope boundaries | phase0,planning,scope | Included capabilities listed
Sub-task |  | List non-goals | Document exclusions such as full autonomous execution, advanced agent marketplace, and over-automation. |  | Define MVP scope boundaries | phase0,planning,scope | Non-goals documented
Sub-task |  | Create scope sign-off sheet | Prepare approval sheet for product owner review. |  | Define MVP scope boundaries | phase0,planning,scope | Scope sign-off captured
Story |  | Define core use cases | Capture real operating scenarios the platform must support for initial launch. | 0.1 Product Vision & Scope Finalization |  | phase0,planning,usecases | At least 3 use cases documented with inputs, outputs, and stakeholders
Sub-task |  | Document B2B lead scoring journey | Map B2B lead from ingestion to recommendation output. |  | Define core use cases | phase0,planning,usecases | B2B journey documented
Sub-task |  | Document SME inbound lead journey | Map SME inbound lead flow with persona-aware scoring context. |  | Define core use cases | phase0,planning,usecases | SME journey documented
Sub-task |  | Document low-intent lead journey | Map low-intent or low-fit lead flow including safe deprioritization. |  | Define core use cases | phase0,planning,usecases | Low-intent journey documented
Story |  | Define success metrics | Create measurable product KPIs for planning and future validation. | 0.1 Product Vision & Scope Finalization |  | phase0,planning,kpi | KPIs documented with definitions and owners
Sub-task |  | Define scoring quality metrics | Document accuracy proxy, consistency, and action relevance metrics. |  | Define success metrics | phase0,planning,kpi | Quality metrics defined
Sub-task |  | Define operational KPIs | Document response time, throughput, retry rate, and failure rate targets. |  | Define success metrics | phase0,planning,kpi | Operational KPIs defined
Sub-task |  | Define business KPIs | Document conversion lift, follow-up prioritization value, and adoption metrics. |  | Define success metrics | phase0,planning,kpi | Business KPIs defined
Epic | 0.2 System Architecture Planning | 0.2 System Architecture Planning | Design modular product architecture, service boundaries, API-first design, and deployment assumptions. |  |  | Epic scope approved
Story |  | Define system layers | Design high-level architecture layers for the platform. | 0.2 System Architecture Planning |  | phase0,architecture,layers | Layered architecture diagram approved
Sub-task |  | Define data layer | Document raw data, enriched data, context, and scoring output storage layers. |  | Define system layers | phase0,architecture,layers | Data layer defined
Sub-task |  | Define intelligence layer | Document persona engine, rating agent, prompt layer, and output schema layer. |  | Define system layers | phase0,architecture,layers | Intelligence layer defined
Sub-task |  | Define orchestration layer | Document orchestration controller, tool invocation, and state tracking responsibilities. |  | Define system layers | phase0,architecture,layers | Orchestration layer defined
Story |  | Define service boundaries | Decide which capabilities are separate services versus internal modules for MVP. | 0.2 System Architecture Planning |  | phase0,architecture,services | Service boundary document approved
Sub-task |  | Define ingestion service boundary | Separate ingestion, validation, and connector logic from downstream scoring. |  | Define service boundaries | phase0,architecture,services | Ingestion service boundary defined
Sub-task |  | Define orchestration and LLM service boundary | Separate orchestration control from LLM wrapper and prompt execution service. |  | Define service boundaries | phase0,architecture,services | LLM service boundary defined
Sub-task |  | Define reporting service boundary | Separate read-model and dashboard APIs from scoring execution path. |  | Define service boundaries | phase0,architecture,services | Reporting service boundary defined
Story |  | Define deployment architecture | Plan how services will run across environments using containers and standard configuration. | 0.2 System Architecture Planning |  | phase0,architecture,devops | Deployment architecture and environment strategy approved
Sub-task |  | Define Docker strategy | Specify that MVP services run in Docker containers with environment-based config. |  | Define deployment architecture | phase0,architecture,devops | Docker strategy defined
Sub-task |  | Define environment layout | Document dev, staging, and production environment expectations. |  | Define deployment architecture | phase0,architecture,devops | Environment layout defined
Sub-task |  | Select cloud readiness assumptions | Document AWS or Azure assumptions for future deployment. |  | Define deployment architecture | phase0,architecture,devops | Cloud assumptions documented
Epic | 0.3 End-to-End Workflow Decomposition | 0.3 End-to-End Workflow Decomposition | Break the system into atomic workflow steps with inputs, outputs, dependencies, and execution mode. |  |  | Epic scope approved
Story |  | Define master workflow | Create the end-to-end platform workflow from lead intake to scored output. | 0.3 End-to-End Workflow Decomposition |  | phase0,workflow,master | Master workflow approved with all stages and transitions
Sub-task |  | List all workflow stages | Document trigger, intake, validation, enrichment, persona, context, LLM, output, and action stages. |  | Define master workflow | phase0,workflow,master | Stages listed
Sub-task |  | Create stage transition map | Document which step triggers the next step and under which conditions. |  | Define master workflow | phase0,workflow,master | Transition map created
Sub-task |  | Create workflow table | Prepare step-by-step table with owner, type, input, output, and dependency columns. |  | Define master workflow | phase0,workflow,master | Workflow table completed
Story |  | Define step-level I/O contracts | Specify input and output payloads for every atomic workflow step. | 0.3 End-to-End Workflow Decomposition |  | phase0,workflow,contracts | I/O contract sheet completed for all workflow steps
Sub-task |  | Define input payloads | Specify required JSON shape or data object structure for each workflow stage. |  | Define step-level I/O contracts | phase0,workflow,contracts | Inputs specified
Sub-task |  | Define output payloads | Specify response shape and status object for each stage. |  | Define step-level I/O contracts | phase0,workflow,contracts | Outputs specified
Sub-task |  | Define failure cases | Document expected failures and fallback outcomes per stage. |  | Define step-level I/O contracts | phase0,workflow,contracts | Failure cases documented
Story |  | Define sync vs async workflow strategy | Decide which steps are synchronous, asynchronous, or parallelizable. | 0.3 End-to-End Workflow Decomposition |  | phase0,workflow,execution | Sync/async execution map approved
Sub-task |  | Classify real-time steps | Mark scoring, response formatting, and user-facing response steps as real-time where needed. |  | Define sync vs async workflow strategy | phase0,workflow,execution | Real-time steps classified
Sub-task |  | Classify async steps | Mark enrichment, scraping, and non-blocking analytics steps as async. |  | Define sync vs async workflow strategy | phase0,workflow,execution | Async steps classified
Sub-task |  | Identify parallel execution opportunities | Document steps that can run simultaneously without dependency conflicts. |  | Define sync vs async workflow strategy | phase0,workflow,execution | Parallel steps identified
Epic | 0.4 Agent vs Automation Mapping | 0.4 Agent vs Automation Mapping | Determine what is deterministic automation, what needs an LLM agent, and how tools support both. |  |  | Epic scope approved
Story |  | Classify workflow steps by execution type | Classify each workflow step as automation, agent, or hybrid. | 0.4 Agent vs Automation Mapping |  | phase0,agents,mapping | All workflow steps tagged by execution type
Sub-task |  | Tag deterministic steps | Mark validation, normalization, connector calls, and static business rules as automation. |  | Classify workflow steps by execution type | phase0,agents,mapping | Automation steps tagged
Sub-task |  | Tag agent-driven steps | Mark persona reasoning, rating, and nuanced recommendation steps as agent-driven. |  | Classify workflow steps by execution type | phase0,agents,mapping | Agent steps tagged
Sub-task |  | Tag hybrid steps | Mark steps combining deterministic computation with LLM judgment as hybrid. |  | Classify workflow steps by execution type | phase0,agents,mapping | Hybrid steps tagged
Story |  | Define required agents and responsibilities | Define minimal agent set and ensure roles do not overlap. | 0.4 Agent vs Automation Mapping |  | phase0,agents,design | Agent responsibility sheet approved
Sub-task |  | Define Persona Agent | Document inputs, logic expectation, outputs, and invocation conditions for Persona Agent. |  | Define required agents and responsibilities | phase0,agents,design | Persona Agent defined
Sub-task |  | Define Rating Agent | Document inputs, score output, reasoning output, and confidence output for Rating Agent. |  | Define required agents and responsibilities | phase0,agents,design | Rating Agent defined
Sub-task |  | Define future optional agents | Document Recommendation Agent or Workflow Agent as future extensions, not MVP blockers. |  | Define required agents and responsibilities | phase0,agents,design | Future agents documented
Story |  | Define tool layer for agents | Specify tools that agents can call instead of directly touching systems. | 0.4 Agent vs Automation Mapping |  | phase0,agents,tools | Tool catalog approved
Sub-task |  | Define data retrieval tools | Specify tools for fetching lead, company, and engagement data. |  | Define tool layer for agents | phase0,agents,tools | Data tools defined
Sub-task |  | Define enrichment tools | Specify tools for domain lookup, company info enrichment, and context fetch. |  | Define tool layer for agents | phase0,agents,tools | Enrichment tools defined
Sub-task |  | Define agent access constraints | Specify that agents do not directly access database or secrets; they only use approved tools. |  | Define tool layer for agents | phase0,agents,tools | Access constraints documented
Epic | 0.5 LLM Interaction & Prompt Strategy | 0.5 LLM Interaction & Prompt Strategy | Define prompt templates, LLM input and output contracts, guardrails, and cost-safe execution strategy. |  |  | Epic scope approved
Story |  | Define prompt template framework | Create standard prompt structure for all LLM interactions. | 0.5 LLM Interaction & Prompt Strategy |  | phase0,llm,prompts | Prompt template framework approved and testable
Sub-task |  | Define prompt sections | Create SYSTEM, CONTEXT, TASK, and OUTPUT FORMAT sections for every LLM prompt. |  | Define prompt template framework | phase0,llm,prompts | Prompt sections defined
Sub-task |  | Create sample B2B prompt | Prepare sample prompt for B2B lead scoring context. |  | Define prompt template framework | phase0,llm,prompts | B2B prompt created
Sub-task |  | Create sample SME prompt | Prepare sample prompt for SME lead with fragmented context. |  | Define prompt template framework | phase0,llm,prompts | SME prompt created
Story |  | Define strict LLM input and output schema | Ensure all LLM interactions are structured and machine-consumable. | 0.5 LLM Interaction & Prompt Strategy |  | phase0,llm,schema | Input and output JSON schema approved
Sub-task |  | Define LLM input JSON contract | Specify fields passed to LLM including lead, company, persona, behavior, and derived metrics. |  | Define strict LLM input and output schema | phase0,llm,schema | Input contract defined
Sub-task |  | Define LLM output JSON contract | Specify score, reasoning, confidence, and recommended_action fields. |  | Define strict LLM input and output schema | phase0,llm,schema | Output contract defined
Sub-task |  | Define schema validation rules | Document how malformed JSON or missing keys are rejected or retried. |  | Define strict LLM input and output schema | phase0,llm,schema | Validation rules defined
Story |  | Define LLM operational safeguards | Plan retries, fallback models, caching, logging, and cost controls. | 0.5 LLM Interaction & Prompt Strategy |  | phase0,llm,ops | Operational safeguards documented
Sub-task |  | Define retry strategy | Specify retry behavior for timeout, invalid JSON, and transient API failures. |  | Define LLM operational safeguards | phase0,llm,ops | Retry policy defined
Sub-task |  | Define fallback model strategy | Specify backup model or degraded mode if primary LLM fails. |  | Define LLM operational safeguards | phase0,llm,ops | Fallback strategy defined
Sub-task |  | Define prompt caching and token monitoring | Document cache strategy, token budgets, and cost tracking requirements. |  | Define LLM operational safeguards | phase0,llm,ops | Caching and cost controls defined
Epic | 0.6 Client Onboarding Workflow Design | 0.6 Client Onboarding Workflow Design | Design how a new client gets configured, connected, validated, and marked ready for scoring. |  |  | Epic scope approved
Story |  | Define end-to-end onboarding flow | Design the full onboarding journey from account creation to platform readiness. | 0.6 Client Onboarding Workflow Design |  | phase0,workflow,onboarding | Onboarding journey documented with readiness criteria
Sub-task |  | Map onboarding stages | Document account creation, organization setup, persona setup, connector setup, and readiness check stages. |  | Define end-to-end onboarding flow | phase0,workflow,onboarding | Stages mapped
Sub-task |  | Define onboarding inputs | Document required onboarding fields such as business type, industry, target audience, and data sources. |  | Define end-to-end onboarding flow | phase0,workflow,onboarding | Inputs documented
Sub-task |  | Define onboarding completion criteria | Document when onboarding is considered complete and scoring can begin. |  | Define end-to-end onboarding flow | phase0,workflow,onboarding | Completion criteria defined
Story |  | Define client configuration schema | Plan how client-level settings will be captured and stored. | 0.6 Client Onboarding Workflow Design |  | phase0,workflow,onboarding,config | Client config schema approved
Sub-task |  | Define business profile fields | Specify industry, business model, geography, and target market fields. |  | Define client configuration schema | phase0,workflow,onboarding,config | Business profile fields defined
Sub-task |  | Define persona and scoring preference fields | Specify persona options, weighting preferences, and output preferences. |  | Define client configuration schema | phase0,workflow,onboarding,config | Preference fields defined
Sub-task |  | Define default and custom settings behavior | Document default values and what clients can override. |  | Define client configuration schema | phase0,workflow,onboarding,config | Default/custom behavior documented
Story |  | Define onboarding DevOps controls | Plan operational controls needed to support onboarding workflow reliably. | 0.6 Client Onboarding Workflow Design |  | phase0,workflow,onboarding,devops | Onboarding operational controls documented
Sub-task |  | Define onboarding logs | Document event logging for each onboarding stage. |  | Define onboarding DevOps controls | phase0,workflow,onboarding,devops | Logging plan documented
Sub-task |  | Define feature flag strategy | Document how client-level modules can be enabled or disabled safely. |  | Define onboarding DevOps controls | phase0,workflow,onboarding,devops | Feature flags documented
Sub-task |  | Define onboarding failure alerts | Document how setup failures trigger alerts or operator review. |  | Define onboarding DevOps controls | phase0,workflow,onboarding,devops | Failure alerts documented
Epic | 0.7 Orchestration Workflow Design | 0.7 Orchestration Workflow Design | Design the orchestration controller, execution state model, retries, queueing, and monitoring for the platform. |  |  | Epic scope approved
Story |  | Define orchestration master pipeline | Design the controller-driven execution pipeline from trigger to output. | 0.7 Orchestration Workflow Design |  | phase0,workflow,orchestration | Orchestration pipeline design approved
Sub-task |  | Map controller flow | Document how controller invokes fetch, validate, enrich, persona, context, LLM, and output stages. |  | Define orchestration master pipeline | phase0,workflow,orchestration | Controller flow mapped
Sub-task |  | Define state model | Document pending, running, failed, completed, and partial states for execution. |  | Define orchestration master pipeline | phase0,workflow,orchestration | State model defined
Sub-task |  | Define handoff contracts | Specify payload handoff between each stage of orchestration. |  | Define orchestration master pipeline | phase0,workflow,orchestration | Handoff contracts defined
Story |  | Define orchestration failure handling | Plan retries, timeouts, and fallback behavior per orchestration step. | 0.7 Orchestration Workflow Design |  | phase0,workflow,orchestration,reliability | Failure handling matrix approved
Sub-task |  | Define timeout thresholds | Specify maximum allowed execution time for external APIs and LLM calls. |  | Define orchestration failure handling | phase0,workflow,orchestration,reliability | Timeouts defined
Sub-task |  | Define retry logic | Specify retry count and backoff rules for recoverable failures. |  | Define orchestration failure handling | phase0,workflow,orchestration,reliability | Retry logic defined
Sub-task |  | Define degraded-mode behavior | Document how system responds when enrichment or LLM is unavailable. |  | Define orchestration failure handling | phase0,workflow,orchestration,reliability | Degraded mode defined
Story |  | Define orchestration DevOps strategy | Plan queueing, worker model, job IDs, and monitoring for orchestration. | 0.7 Orchestration Workflow Design |  | phase0,workflow,orchestration,devops | Operational orchestration plan approved
Sub-task |  | Define queueing mechanism | Document whether async execution uses job queue or worker pool for enrichment and batch tasks. |  | Define orchestration DevOps strategy | phase0,workflow,orchestration,devops | Queueing mechanism defined
Sub-task |  | Define job tracking strategy | Document unique job ID, step-level status, and trace correlation requirements. |  | Define orchestration DevOps strategy | phase0,workflow,orchestration,devops | Job tracking strategy defined
Sub-task |  | Define monitoring dashboard metrics | Specify success rate, failure rate, retry count, and average stage time metrics. |  | Define orchestration DevOps strategy | phase0,workflow,orchestration,devops | Monitoring metrics defined
Epic | 0.8 Data Acquisition & Scraping Workflow Design | 0.8 Data Acquisition & Scraping Workflow Design | Design data acquisition strategy for internal data, external APIs, and scraping-based enrichment workflows. |  |  | Epic scope approved
Story |  | Define data source strategy | Identify and classify all data sources needed for enrichment. | 0.8 Data Acquisition & Scraping Workflow Design |  | phase0,workflow,data-acquisition | Data source catalog approved
Sub-task |  | List internal sources | Document CRM, CSV, platform events, and internal lead history sources. |  | Define data source strategy | phase0,workflow,data-acquisition | Internal sources listed
Sub-task |  | List external sources | Document public APIs, company websites, directories, and social signal sources. |  | Define data source strategy | phase0,workflow,data-acquisition | External sources listed
Sub-task |  | Classify source reliability | Document confidence and freshness expectations for each source. |  | Define data source strategy | phase0,workflow,data-acquisition | Reliability classified
Story |  | Define scraping workflow | Design how company information is fetched and converted into structured enrichment data. | 0.8 Data Acquisition & Scraping Workflow Design |  | phase0,workflow,scraping | Scraping workflow design approved
Sub-task |  | Define scraping inputs | Document minimum inputs such as domain, company name, or profile URL. |  | Define scraping workflow | phase0,workflow,scraping | Scraping inputs defined
Sub-task |  | Define scraping outputs | Document output schema including industry, size, offerings, market signals, and evidence fields. |  | Define scraping workflow | phase0,workflow,scraping | Scraping outputs defined
Sub-task |  | Define merge logic | Document how scraped data merges with client-provided or CRM data without corrupting source truth. |  | Define scraping workflow | phase0,workflow,scraping | Merge logic defined
Story |  | Define scraping DevOps controls | Plan rate limits, scheduling, and operational safeguards for scraping flows. | 0.8 Data Acquisition & Scraping Workflow Design |  | phase0,workflow,scraping,devops | Scraping operational controls documented
Sub-task |  | Define scheduler strategy | Document cron or scheduled job strategy for refresh-based scraping. |  | Define scraping DevOps controls | phase0,workflow,scraping,devops | Scheduler strategy defined
Sub-task |  | Define throttling and rate limits | Document rate limiting and backoff to avoid abuse or blocking. |  | Define scraping DevOps controls | phase0,workflow,scraping,devops | Rate limits defined
Sub-task |  | Define scrape failure logging | Document how scrape failures, partial data, and parse errors are logged and traced. |  | Define scraping DevOps controls | phase0,workflow,scraping,devops | Scrape logging plan defined
Epic | 0.9 Context Construction Workflow Design | 0.9 Context Construction Workflow Design | Define how raw lead and company data is transformed into LLM-ready context objects. |  |  | Epic scope approved
Story |  | Define context object schema | Create the structured context object that is sent to the LLM. | 0.9 Context Construction Workflow Design |  | phase0,data,context | Context schema approved
Sub-task |  | Define core sections | Specify lead, company, persona, engagement, derived metrics, and evidence sections. |  | Define context object schema | phase0,data,context | Core sections defined
Sub-task |  | Define mandatory versus optional fields | Document which fields must exist and which can be null or fallback values. |  | Define context object schema | phase0,data,context | Field optionality defined
Sub-task |  | Create sample context objects | Prepare sample JSON for B2B, SMB, and low-context lead scenarios. |  | Define context object schema | phase0,data,context | Sample context objects created
Story |  | Define transformation and feature rules | Plan normalization and derived feature creation before LLM execution. | 0.9 Context Construction Workflow Design |  | phase0,data,features | Transformation rules approved
Sub-task |  | Define normalization rules | Standardize company names, categories, timestamps, and missing values. |  | Define transformation and feature rules | phase0,data,features | Normalization rules defined
Sub-task |  | Define derived metrics | Document engagement score, recency, frequency, and fit-related derived metrics. |  | Define transformation and feature rules | phase0,data,features | Derived metrics defined
Sub-task |  | Define prompt inclusion rules | Decide what information enters prompt and what remains outside the prompt for logging or reporting only. |  | Define transformation and feature rules | phase0,data,features | Prompt inclusion rules defined
Story |  | Define context DevOps controls | Plan caching, versioning, and validation controls for context objects. | 0.9 Context Construction Workflow Design |  | phase0,data,context,devops | Context operational controls documented
Sub-task |  | Define context versioning strategy | Document how context schema versions are tracked across prompt changes. |  | Define context DevOps controls | phase0,data,context,devops | Versioning strategy defined
Sub-task |  | Define context caching strategy | Document where and how context objects are cached to avoid recomputation. |  | Define context DevOps controls | phase0,data,context,devops | Caching strategy defined
Sub-task |  | Define validation logging | Document context build validation errors and trace logging requirements. |  | Define context DevOps controls | phase0,data,context,devops | Validation logging defined
Epic | 0.10 Security Planning | 0.10 Security Planning | Plan authentication, authorization, input safety, secrets handling, encryption, and LLM data protection. |  |  | Epic scope approved
Story |  | Define platform authentication and RBAC | Plan how users and services authenticate and what roles can access which data. | 0.10 Security Planning |  | phase0,security,auth | Authentication and RBAC policy approved
Sub-task |  | Define auth mechanism | Document JWT or OAuth-style authentication for MVP services. |  | Define platform authentication and RBAC | phase0,security,auth | Auth mechanism defined
Sub-task |  | Define role matrix | Document admin, analyst, client, and operator permissions per module. |  | Define platform authentication and RBAC | phase0,security,auth | Role matrix defined
Sub-task |  | Define API access rules | Document which APIs require auth, elevated role, or tenant restrictions. |  | Define platform authentication and RBAC | phase0,security,auth | API access rules defined
Story |  | Define data and API protection controls | Plan safe handling of inputs, transport, secrets, and auditability. | 0.10 Security Planning |  | phase0,security,api | Security control checklist approved
Sub-task |  | Define input sanitization rules | Document payload validation and SQL injection safe handling patterns. |  | Define data and API protection controls | phase0,security,api | Input sanitization rules defined
Sub-task |  | Define encryption policy | Document HTTPS/TLS for transit and encryption-at-rest assumptions for stored data. |  | Define data and API protection controls | phase0,security,api | Encryption policy defined
Sub-task |  | Define secrets management plan | Document use of secrets manager or environment isolation for credentials and API keys. |  | Define data and API protection controls | phase0,security,api | Secrets plan defined
Story |  | Define LLM data safety controls | Prevent sensitive data leakage and unsafe context transmission to LLMs. | 0.10 Security Planning |  | phase0,security,llm | LLM data safety policy approved
Sub-task |  | Define PII masking rules | Document what data must be masked or removed before LLM calls. |  | Define LLM data safety controls | phase0,security,llm | PII masking rules defined
Sub-task |  | Define prompt logging sanitization | Document how prompts and responses are logged without exposing sensitive fields. |  | Define LLM data safety controls | phase0,security,llm | Sanitized logging rules defined
Sub-task |  | Define audit logging requirements | Document access and scoring event audit fields required for compliance and debugging. |  | Define LLM data safety controls | phase0,security,llm | Audit requirements defined
Epic | 0.11 Observability & Scalability Planning | 0.11 Observability & Scalability Planning | Plan logging, tracing, monitoring, alerting, autoscaling, and backup strategy for market-ready operations. |  |  | Epic scope approved
Story |  | Define end-to-end observability strategy | Plan how every lead and job is traceable across the platform. | 0.11 Observability & Scalability Planning |  | phase0,observability,logging | Observability plan approved
Sub-task |  | Define step-level logging | Document request, response, error, and state-change logs per pipeline step. |  | Define end-to-end observability strategy | phase0,observability,logging | Logging plan defined
Sub-task |  | Define trace correlation strategy | Document how lead IDs and job IDs connect logs across services. |  | Define end-to-end observability strategy | phase0,observability,logging | Trace correlation defined
Sub-task |  | Define replay/debug strategy | Document how failed jobs can be replayed for troubleshooting. |  | Define end-to-end observability strategy | phase0,observability,logging | Replay strategy defined
Story |  | Define monitoring and alerting strategy | Plan runtime metrics, thresholds, and proactive alerts. | 0.11 Observability & Scalability Planning |  | phase0,observability,monitoring | Monitoring and alerts plan approved
Sub-task |  | Define core service metrics | Document latency, throughput, queue depth, LLM failure rate, and connector failure rate metrics. |  | Define monitoring and alerting strategy | phase0,observability,monitoring | Service metrics defined
Sub-task |  | Define alert thresholds | Document thresholds for high latency, failed jobs, and degraded LLM or scraping performance. |  | Define monitoring and alerting strategy | phase0,observability,monitoring | Alert thresholds defined
Sub-task |  | Define ownership for alerts | Document who receives which alert and expected response model. |  | Define monitoring and alerting strategy | phase0,observability,monitoring | Alert ownership defined
Story |  | Define scalability and resilience strategy | Plan capacity, autoscaling, and backup expectations for market-ready deployment. | 0.11 Observability & Scalability Planning |  | phase0,scalability,resilience | Scalability strategy approved
Sub-task |  | Define horizontal scaling assumptions | Document which services scale independently, especially orchestration, enrichment, and LLM wrapper services. |  | Define scalability and resilience strategy | phase0,scalability,resilience | Scaling assumptions defined
Sub-task |  | Define autoscaling triggers | Document load-based autoscaling triggers for worker or API services. |  | Define scalability and resilience strategy | phase0,scalability,resilience | Autoscaling triggers defined
Sub-task |  | Define backup and recovery plan | Document database backup frequency, retention, and recovery assumptions. |  | Define scalability and resilience strategy | phase0,scalability,resilience | Backup and recovery plan defined